## FAC Tracker
Site Name | FAC Date | O&M Contractor | Task | Sub-Task | Responsibility | Accepted By(AM) | Dates as per testing | Remarks | Status | 2025 | [51 empty] | 2026 | [52 empty] | 2027 | [51 empty] | 2028
[10 empty] | Dec | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  | Sep |  |  |  |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Dec | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  | Jun |  |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | Mar |  |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  | Aug |  |  |  |  | Sep |  |  |  | Oct |  |  |  | Nov |  |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun |  |  |  | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec
[10 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 53 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38 | 39 | 40 | 41 | 42 | 43 | 44 | 45 | 46 | 47 | 48 | 49 | 50 | 51 | 52
Zonnepark Groense bos ¦ NL ¦ FAC: 13-Feb-2027 ¦ O&M: Ecorus
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2026-01-13
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit |  |  | Done | bar: Jan 3
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit |  |  | Done | bar: Jan 4
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob |  |  | Done | bar: Jan 5 to Feb 8
|  |  |  | Defect rectification verification | Construction Manager | Rob |  |  | Done | bar: Feb 9 to Mar 10
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita |  |  | Done | bar: Jan 5 to Feb 7
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita |  |  | Done | bar: Feb 8
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob |  |  | Done | bar: Jan 5 to Feb 6
|  |  |  | Payment confirmation | Finance Team | Rob |  |  | Done | bar: Feb 7
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita |  |  | Done | bar: Mar 11 to Mar 13
|  |  |  | Scope of Work | Construction Manager | AM Team |  |  | Done | bar: Mar 11 to Mar 13
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team |  |  | Done | bar: Mar 14 to Apr 17
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita |  |  | Done | bar: Apr 18 to May 19
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties |  |  |  |  | Done | bar: May 20
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2027-02-13
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Jan 3 to Jan 4
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Feb 5 to Feb 6
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Feb 7
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Feb 7
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Feb 8 to Mar 9
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Feb 8 to Mar 9
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Mar 10 to Mar 12
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Mar 10 to Mar 13
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Apr 14
Echt-Susteren ¦ NL ¦ FAC: 01-Dec-2025 ¦ O&M: Aton
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2024-11-01 |  | Done
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit |  |  | Done
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit |  |  | Done
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob |  |  | Done
|  |  |  | Defect rectification verification | Construction Manager | Rob |  |  | Done
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita |  |  | Done
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita |  |  | Done
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob |  |  | Done
|  |  |  | Payment confirmation | Finance Team | Rob |  |  | Done
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita |  |  | Done | bar: Dec 1 to Jan 2
|  |  |  | Scope of Work | Construction Manager | AM Team |  |  | Done | bar: Dec 1 to Jan 3
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team |  |  | Done | bar: Jan 4 to Feb 7
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita |  |  | Done | bar: Feb 8 to Feb 9
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties | bar: Mar 10
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2025-11-01
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Nov 45 to Nov 46
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Nov 47 to Nov 48
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Dec 49
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Dec 49
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Dec 50 to Dec 51
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Dec 50 to Dec 51
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Dec 52 to Jan 2
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Dec 52 to Jan 3
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Jan 4
Venray ¦ NL ¦ FAC: 01-Dec-2025 ¦ O&M: Aton
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2024-11-01
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit |  |  | Done
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit |  |  | Done
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob |  |  | Done
|  |  |  | Defect rectification verification | Construction Manager | Rob |  |  | Done
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita |  |  | Done
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita |  |  | Done
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob |  |  | Done
|  |  |  | Payment confirmation | Finance Team | Rob |  |  | Done
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita |  |  | Done | bar: Dec 1 to Jan 2
|  |  |  | Scope of Work | Construction Manager | AM Team |  |  | Done | bar: Dec 1 to Jan 3
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team |  |  | Done | bar: Jan 4 to Feb 7
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita |  |  | Done | bar: Feb 8 to Feb 9
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties |  |  |  |  | Done | bar: Mar 10
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2025-11-01
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Nov 45 to Nov 46
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Nov 47 to Nov 48
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Dec 49
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Dec 49
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Dec 50 to Dec 51
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Dec 50 to Dec 51
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Dec 52 to Jan 2
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Dec 52 to Jan 3
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Jan 4
Tinte ¦ NL ¦ FAC: 01-Mar-2026 ¦ O&M: Aton
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2025-02-01
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit |  |  | Done | bar: Jan 5
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit |  |  | Done | bar: Feb 6
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob |  |  | Done | bar: Feb 7 to Mar 10
|  |  |  | Defect rectification verification | Construction Manager | Rob |  |  | Done | bar: Mar 11 to Mar 12
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita |  |  | Done | bar: Feb 7 to Feb 9
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita |  |  | Done | bar: Mar 10
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob |  |  | Done | bar: Feb 7 to Feb 8
|  |  |  | Payment confirmation | Finance Team | Rob |  |  | Done | bar: Feb 9
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita |  |  | Done | bar: Mar 13 to Apr 15
|  |  |  | Scope of Work | Construction Manager | AM Team |  |  | Done | bar: Mar 13 to Apr 15
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team |  |  | Done | bar: Apr 16 to May 19
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita |  |  | Done | bar: May 20 to May 21
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties |  |  |  |  | Done | bar: May 22
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2026-02-01
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Feb 6 to Feb 7
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Feb 8 to Feb 9
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Mar 10
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Mar 10
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Mar 11 to Mar 12
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Mar 11 to Mar 12
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Mar 13 to Apr 15
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Mar 13 to Apr 16
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Apr 17
NOP Noord ¦ NL ¦ FAC: 24-Sep-2027 ¦ O&M: Ecorus
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2026-08-24
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit | bar: Aug 35
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit | bar: Aug 36
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob | bar: Sep 37 to Sep 40
|  |  |  | Defect rectification verification | Construction Manager | Rob | bar: Oct 41 to Oct 42
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita | bar: Sep 37 to Sep 39
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita | bar: Sep 40
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob | bar: Sep 37 to Sep 38
|  |  |  | Payment confirmation | Finance Team | Rob | bar: Sep 39
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita | bar: Oct 43 to Nov 45
|  |  |  | Scope of Work | Construction Manager | AM Team | bar: Oct 43 to Nov 45
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team | bar: Nov 46 to Nov 49
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita | bar: Dec 50 to Dec 51
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties | bar: Dec 52
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2027-08-24
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Aug 35 to Sep 36
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Sep 37 to Sep 38
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Sep 39
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Sep 39
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Oct 40 to Oct 41
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Oct 40 to Oct 41
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Oct 42 to Nov 44
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Oct 42 to Nov 45
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Nov 46
NOP Midden ¦ NL ¦ FAC: 24-Sep-2027 ¦ O&M: Ecorus
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2026-08-24
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit | bar: Aug 35
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit | bar: Aug 36
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob | bar: Sep 37 to Sep 40
|  |  |  | Defect rectification verification | Construction Manager | Rob | bar: Oct 41 to Oct 42
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita | bar: Sep 37 to Sep 39
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita | bar: Sep 40
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob | bar: Sep 37 to Sep 38
|  |  |  | Payment confirmation | Finance Team | Rob | bar: Sep 39
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita | bar: Oct 43 to Nov 45
|  |  |  | Scope of Work | Construction Manager | AM Team | bar: Oct 43 to Nov 45
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team | bar: Nov 46 to Nov 49
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita | bar: Dec 50 to Dec 51
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties | bar: Dec 52
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2027-08-24
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Jun 26 to Jul 27
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Jul 28 to Jul 29
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Jul 30
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Jul 30
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Aug 31 to Aug 32
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Aug 31 to Aug 32
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Aug 33 to Aug 35
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Aug 33 to Sep 36
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Sep 37
NOP Zuid ¦ NL ¦ FAC: 24-Sep-2027 ¦ O&M: Ecorus
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2026-08-24
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit | bar: Aug 35
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit | bar: Aug 36
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob | bar: Sep 37 to Sep 40
|  |  |  | Defect rectification verification | Construction Manager | Rob | bar: Oct 41 to Oct 42
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita | bar: Sep 37 to Sep 39
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita | bar: Sep 40
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob | bar: Sep 37 to Sep 38
|  |  |  | Payment confirmation | Finance Team | Rob | bar: Sep 39
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita | bar: Oct 43 to Nov 45
|  |  |  | Scope of Work | Construction Manager | AM Team | bar: Oct 43 to Nov 45
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team | bar: Nov 46 to Nov 49
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita | bar: Dec 50 to Dec 51
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties | bar: Dec 52
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2027-08-24
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Aug 35 to Sep 36
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Sep 37 to Sep 38
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Sep 39
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Sep 39
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Oct 40 to Oct 41
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Oct 40 to Oct 41
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Oct 42 to Nov 44
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Oct 42 to Nov 45
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Nov 46
NOP 4 (4) ¦ NL ¦ FAC: 24-Sep-2027 ¦ O&M: Ecorus
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2026-08-24
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit | bar: Aug 35
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit | bar: Aug 36
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob | bar: Sep 37 to Sep 40
|  |  |  | Defect rectification verification | Construction Manager | Rob | bar: Oct 41 to Oct 42
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita | bar: Sep 37 to Sep 39
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita | bar: Sep 40
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob | bar: Sep 37 to Sep 38
|  |  |  | Payment confirmation | Finance Team | Rob | bar: Sep 39
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita | bar: Oct 43 to Nov 45
|  |  |  | Scope of Work | Construction Manager | AM Team | bar: Oct 43 to Nov 45
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team | bar: Nov 46 to Nov 49
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita | bar: Dec 50 to Dec 51
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties | bar: Dec 52
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2027-08-24
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Aug 35 to Sep 36
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Sep 37 to Sep 38
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Sep 39
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Sep 39
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Oct 40 to Oct 41
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Oct 40 to Oct 41
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Oct 42 to Nov 44
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Oct 42 to Nov 45
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Nov 46
Gorgast Bahn ¦ Germany ¦ FAC: 11-Jul-2027 ¦ O&M: Aton
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2026-06-11
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit | bar: Jun 24
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit | bar: Jun 25
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob | bar: Jun 26 to Jul 29
|  |  |  | Defect rectification verification | Construction Manager | Rob | bar: Jul 30 to Jul 31
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita | bar: Jun 26 to Jul 28
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita | bar: Jul 29
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob | bar: Jun 26 to Jun 27
|  |  |  | Payment confirmation | Finance Team | Rob | bar: Jul 28
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita | bar: Aug 32 to Aug 34
|  |  |  | Scope of Work | Construction Manager | Ankit | bar: Aug 32 to Aug 34
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team | bar: Aug 35 to Sep 38
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita | bar: Sep 39 to Sep 40
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties | bar: Oct 41
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2027-06-11
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Jun 24 to Jun 25
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Jun 26 to Jul 27
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Jul 28
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Jul 28
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Jul 29 to Jul 30
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Jul 29 to Jul 30
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Aug 31 to Aug 33
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Aug 31 to Aug 34
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Aug 35
Gorgast Manschow ¦ Germany ¦ FAC: 23-Jan-2028 ¦ O&M: Aton
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2026-12-23
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit | bar: Dec 52
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit | bar: Dec 53
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob | bar: Jan 1 to Jan 4
|  |  |  | Defect rectification verification | Construction Manager | Rob | bar: Feb 5 to Feb 6
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita | bar: Jan 1 to Jan 3
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita | bar: Jan 4
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob | bar: Jan 1 to Jan 2
|  |  |  | Payment confirmation | Finance Team | Rob | bar: Jan 3
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita | bar: Feb 7 to Mar 9
|  |  |  | Scope of Work | Construction Manager | AM Team | bar: Feb 7 to Mar 9
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team | bar: Mar 10 to Mar 13
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita | bar: Apr 14 to Apr 15
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties | bar: Apr 16
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2027-12-23
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Dec 52 to Jan 1
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Jan 2 to Jan 3
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Jan 4
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Jan 4
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Jan 5 to Feb 6
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Jan 5 to Feb 6
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Feb 7 to Feb 9
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Feb 7 to Mar 10
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Mar 11
Gorgast Gewachshaus ¦ Germany ¦ FAC: 23-Jan-2028 ¦ O&M: Aton
|  |  | ▸ FIRST YEAR TESTING (11 months after PAC) |  |  |  | 2026-12-23
|  |  | PAC signed by both parties — confirmed | Verify PAC certificate is in place | Construction Manager | Ankit | bar: Dec 52
|  |  |  | Confirm prerequisite for first year testing | AM Team | Ankit | bar: Dec 53
|  |  | Contractor obligations fulfilled during DLP | All defects liability obligations discharged (Cl. 13) | Construction Manager | Rob | bar: Jan 1 to Jan 4
|  |  |  | Defect rectification verification | Construction Manager | Rob | bar: Feb 5 to Feb 6
|  |  | Punch list — all items fully closed | Review outstanding punch list items | Construction Manager | Ankit/Ishita | bar: Jan 1 to Jan 3
|  |  |  | Verify no outstanding items remain | Construction Manager | Ankit/Ishita | bar: Jan 4
|  |  | All liquidated damages & indemnities paid | Financial settlement review | Finance Team | Rob | bar: Jan 1 to Jan 2
|  |  |  | Payment confirmation | Finance Team | Rob | bar: Jan 3
|  |  | Works & PV Park comply with all agreement req. | Performance Ratio verification against guaranteed PR | O&M Contractor | Ishita | bar: Feb 7 to Mar 9
|  |  |  | Scope of Work | Construction Manager | AM Team | bar: Feb 7 to Mar 9
|  |  | TA tests, inspections & verifications passed | Schedule 3 Testing Protocol — TA conducts tests | O&M Contractor | AM Team | bar: Mar 10 to Mar 13
|  |  |  | First Year Testing Report preparation | O&M Contractor | Ishita | bar: Apr 14 to Apr 15
|  |  | First Year Testing Certificate signed | Certificate preparation and sign-off by both parties | bar: Apr 16
|  |  | ▸ FINAL ACCEPTANCE CERTIFICATE |  |  |  | 2027-12-23
|  |  | Final Testing conducted | Final Testing 1 month before 2nd anniversary of PAC | O&M Contractor | AM Team | bar: Dec 52 to Jan 1
|  |  |  | Results documented in Final Testing Report | O&M Contractor | AM Team | bar: Jan 2 to Jan 3
|  |  | PAC signed by both parties — confirmed | Confirm PAC prerequisite is in place | Construction Manager | AM Team | bar: Jan 4
|  |  | FYT Certificate signed by both parties | Confirm FYT Certificate prerequisite is in place | Construction Manager | AM Team | bar: Jan 4
|  |  | DLP obligations fulfilled — punch list closed | Clause 13 — zero outstanding items verified | Construction Manager | AM Team | bar: Jan 5 to Feb 6
|  |  | All liquidated damages & indemnities settled | Full financial settlement per agreement | Finance Team | AM Team | bar: Jan 5 to Feb 6
|  |  | Works & PV Park comply with agreement req. | Full technical and contractual compliance confirmed | O&M Contractor | Ankit/Ishita | bar: Feb 7 to Feb 9
|  |  | TA final tests, inspections & verifications passed | Schedule 3 Final Testing Protocol — TA certifies | bar: Feb 7 to Mar 10
|  |  | FAC signed — Final Acceptance Certificate issued | Project formally closed — both parties sign FAC | bar: Mar 11
Northwold ¦ UK ¦ FAC: 01-Nov-2027 ¦ O&M: Metlen
Northwold |  | Metlen | PAC / FAC dates not yet confirmed — tasks pending
Snelleloop ¦ NL ¦ FAC: — ¦ O&M: Aton
Snelleloop | TBC | Aton | PAC / FAC dates not yet confirmed — tasks pending
Merenberg ¦ Germany ¦ FAC: — ¦ O&M: Aton
Merenberg | TBC | Aton | PAC / FAC dates not yet confirmed — tasks pending

## Legend
Category | Color
Prerequisite | ■ Prerequisite
Compliance | ■ Compliance
Closure | ■ Closure
Financial | ■ Financial
Technical | ■ Technical
Testing | ■ Testing
Document | ■ Document
O&M Contractor
Ecorus | Project header
Aton | Project header
Absolute | Project header
Metlen | Project header
Today marker | 14-Jul-2026